## Product Backlog (Scrum)
MoSCoW ID | Product Backlog ID | Source | Priority (M/S/C/W) | User Story ID | User Story Name | User | Scrum Team Assigned | Complexity | Risk/ Impact | R | Business Process | Type | Primary Actors | Secondary Actors | Comments | Acceptance Criteria | Completeness Criteria | User Acceptance Test Case ID | Comments
1 | 1 | Standard document | High | USGreatOutdoor:001 | Design Documentation for Backend application | Sreenath | Amrita | Average | Low | RD:1 Application SetUp | RD:Business Requirement Doc | Non-Functional |  |  |  |  | 22 hrs | Design is fullfilled agaist Business requirement
2 | 2 | Standard document |  | USGreatOutdoor:002 | Test Plan | Sreenath | Amrita | Average | Low | RD:2 Test plan | RD:Business Requirement Doc | Non-Functional |  |  |  |  | 8 hrs | Check the test case is fullfiled with user accepance criteria document
3 | 3 | Standard document | High | USGreatOutdoor:003 | Bootstrapping the project | Sreenath | Amrita | Simple | Low | RD:3 Bootstraping | RD: GreatoutdoorDocumen_ver1 | Non-Functional |  |  |  |  | 4 hrs | Checking Against the Application Setup and ensure the equired dependencies and run the main code and check the server is tarted without errors
4 | 4 | Work session | High | USGreatOutdoor:004 | Entity Class and TableDEsign and Populating the data | Sreenath | Amrita | Complex | Low | RD4: Entity Class Design and RD3: Table Design | RD: GreatoutdoorDocument_ver2 | Functional |  |  |  |  | 8 hrs | Checking against the Table design in RD
5 | 5 | Work session | High | USGreatOutdoor:005 | Displaying product detail and other product related for the given search | Sreenath | Amrita | Average | Low | RD 5: Displaying the products | RD: GreatoutdoorDocument_ver3 | Functional |  |  |  |  | 16 hrs | TC_Service_01,TC_DAO_01, TC_UI_01
6 | 6 | Work session | High | USGreatOutdoor:006 | Adding the selected item to the cart | Sreenath | Amrita | Complex | Low | RD6: Adding items to cart | RD: GreatoutdoorDocument_ver4 | Functional |  |  |  |  | 7 hrs | TC_Service_02,TC_DAO_02, TC_UI_03
7 | 7 | Work session | High | USGreatOutdoor:007 | Showing wishlist to the user | Sreenath | Amrita | Average | Low | RD7:Showing wishlist | RD: GreatoutdoorDocument_ver5 | Functional |  |  |  |  | 5 hrs | TC_Service_02,TC_DAO_02, TC_UI_04
8 | 8 | Work session | High | USGreatOutdoor:008 | Address Management by user | Sreenath | Amrita | Complex | High | RD:Add ,Delete and update Address by user | RD: GreatoutdoorDocument_ver6 | Functional |  |  |  |  | 16 hrs | TC_Service_02,TC_DAO_02, TC_UI_05
9 | 9 | Work session | High | USGreatOutdoor:009 | Cancel Product by user | Sreenath | Amrita | Average | Average | RD9: Cancel Product | RD: GreatoutdoorDocument_ver7
10 | 10 | Work session | High | USGreatOutdoor:009 | Showing growth report | Sreenath | Amrita | Average | Low | RD9: showing growth report | RD: GreatoutdoorDocumen_ver9 | Functional |  |  |  |  | 10 hrs | TC_Service_02,TC_DAO_02, TC_UI_06
9 | 11 | Work session | High | USGreatOutdoor:010 | showing delivery report | Sreenath | Amrita | Average | Low | RD10: Delivery report | RD: GreatoutdoorDocumen_ver10 | Functional |  |  |  |  | 5 hrs | TC_Service_02,TC_DAO_02, TC_UI_07
10
12
14
Sprint 2 | Sprint 2
15 | 12 | Standard document | High | USGreatOutdoor:007 | Design Documentation fo Angular application | Sreenath | Amrita | Complex | Low | RD): Business Requirement DOc | RD: Business Requirement and User accepatance Criteria | Non Functional
| 13 | Standard document | High | USGreatOutdoor:008 | Test Plan | Sreenath | Amrita | Complex | Low | RD): Business Requirement DOc | RD: Business Requirement and User accepatance Criteria | Non Functional
16 | 14 | Standard document | High | USGreatOutdoor:009 | Design a home page having standard menus | Sreenath | Amrita | Complex | Low | RD): Business Requirement DOc | RD: Business Requirement and User accepatance Criteria | Non Functional
17 | 15 | Standard document | High | USGreatOutdoor:010 | Add Security To Login Page | Sreenath | Amrita | Complex | Low | RD): Business Requirement DOc | RD: Business Requirement and User accepatance Criteria | Non Functional
19 | 21
20 | 22
21 | 23
22 | 24
23 | 25
24 | 26
25 | 27
26 | 28
27 | 29
28 | 30
29 | 31
30 | 32
33
31 | 34
32 | 35
33 | 36
34 | 37
35 | 38
36 | 39
37 | 40
38 | 41
39 | 42
40 | 43
41 | 44
42 | 45
43 | 46
44 | 47
45 | 48
46 | 49
When using a Scrum approach to project management, use this sheet to document the Product Backlog, as captured in User Stories.
Note on A3: This column is used to Link back to the Full MoSCoW list for the project (RD.045 sheet).
Note on B3: This column is used to uniquely identify each row on this worksheet. User Stories in a given Sprint are traced back to the Product Backlog using the User Story ID to the details on the Sprint Backlog
Note on C3: This column documents the source from which the expanded requirement came (e.g., statement of work, change request, work session, standards document etc.).
Note on D3: Column to prioritize requirements using MoSCoW) - Must Have, Should Have, Could Have, Won't Have
Note on E3: Column for uniquely identifying the use case, Originates from Use case Model [RA.023] When used Corresponds to a use case number on the Use Case Catalog sheet. Note - Requirements satisfied by COTS applications that are defined in SOW are assigned a use case in order to create traceability. Not required for requirements satisfied by the COTS App that are not in SOW.
Note on F3: Brief description of the requirements necessary to fulfill the objective
Note on G3: Column used to identify owner of requirement as defined by SOW and/or supporting documentation. Defined assumptions are treated as requirements owned by designated party.
Note on H3: Column used to identify owner of requirement as defined by SOW and/or supporting documentation. Defined assumptions are treated as requirements owned by designated party.
Note on I3: Complexity of the functional requirement. Very Simple Simple Average Complex Very Complex
Note on J3: Technical, Organizational, External project risk associated with the requirement. This is further detailed in the Project Risk Management Plan. What is the probability that something will go wrong in meeting the requirement? A risk might happen, or it might not; there is some uncertainty. Use H (High), M (Medium), L (Low).
Note on K3: Used if reference is needed to another work product that provides further detail of the requirement. Examples include RA.027 Candidate Business Rules, RA.090 Reporting Fit Analysis, RA.027 Use Case Details, RD.070 Audit and Control Requirements), DS.030 Application Set-up Documents.
Note on L3: Column to document the originating process where the process is defined and necessary. For example, a process that originates from either Current Process Model [RD.030] or Future Process Model [RD.011].
Note on M3: Defines whether the User Story is Functional, Non-Functional or Technical type.
Note on N3: Column provides linkage to primary actors defined in RA.023 (Use Case Model) and/or RD.005 (System Context Diagram)
Note on O3: Column provides linkage to secondary actors defined in RA.023 (Use Case Model) and/or RD.005 (System Context Diagram)
Note on P3: Use column for supporting comments.
Note on Q3: Column for defining the agreed upon acceptance criteria
Note on R3: Description of the condition(s) that indicate the requirement has been satisfied.
Note on S3: This column is used to link the User Story to the User Acceptance test scenarios that validate the requirement was satisfied.
Note on T3: This column is used to provide supporting information, such as changes to the original requirement.

## Sprint Backlog 2
Product Backlog ID | User Story ID | User Story Task Step number | Task Step description | Assigned to | Assigned Date | Original Estimate | Adjusted estimate | Status | Actual Effort | Comment | Columns to the right are OPTIONAL depending on the level of rigor applied to the project. | Module or Component ID | Unit Test Scenario ID | System Test Scenario ID | Systems Integration Test Scenario ID
12 | USGreatOutdoor:012 | 1 | Wireframes and story boarding for each task | Kamal | 2020-04-27 | 1 hr | 50 min | complted | 45 min
13 | USGreatOutdoor:013 | 2 | Routing Url List | Amrita | 2020-04-27 | 1 hr | 45 min | complted | 30 min |  | localhost:4200,localhost:8080,localhost:4100,localhost:9000,localhost:8082
|  | 3 | Data classes details | Tanushree | 2020-04-28 | 2 hrs | 1.5 hr | complted | 70 min
|  | 4 | Angular service | Mohit | 2020-04-28 | 1.5 hr | 1 hr | complted | 50 min
|  | 5 | Components details | Ajesh | 2020-04-29 | 1.5 hr | 1 hr | complted | 45 min
|  | 6 | Detail about the security | Amrita | 2020-04-29 | 3 hr | 3 hrs | complted | 2hr 45 min
14 | USGreatOutdoor:14 | 1 | Login and Logout | Amrita | 2020-04-30 | 4 hr | 3 hrs | complted | 3 hr
|  | 2 | Registration | Amrita | 2020-05-01 | 3 hr | 2.5 hr | complted | 2hr 20 min
|  | 3 | Test Plan for displaying schedule | Mohit | 2020-04-30 | 1 hr | 45 min | complted | 50min
|  | 4 | Designing menu in template | Mohit | 2020-05-01 | 2 hrs | 2 hr | complted | 1hr 50 min
|  | 5 | Adding Routing details | Ajesh | 2020-05-01 | 2 hrs | 2 hr | complted | 2 hrs
15 | USGreatOutdoor:15 | 1 | Adding Auth Guard | Amrita | 2020-05-02 | 3 hr | 3 hrs | complted
|  | 2 | Adding Local Session | Amrita | 2020-05-03 | 2.5 hrs | 2 hr | complted | 2 hr
List User Story steps that were not completed at Sprint End
Note on A3: This column is used to trace each row of this spreadsheet back to a specific row on the MoSCoW List worksheet.
Note on B3: This column is used to document the Use Case Identifier.
Note on D3: Task Step description. You would only use this column when detailing User Stories using the short form as described in RA.021. If you are using the long form of the User Stories template you may eliminate this column.
Note on E3: List the Scrum team members assigned to this task.
Note on F3: Column is used to document the date the task was assigned
Note on G3: Use this column to provide Initial Scrum team estimate of effort for the task step to be completed, may be numbers of days or hours.
Note on H3: Adjusted estimate after the Sprint has begun
Note on I3: Task status: Started In Progress Completed Cancelled Deferred to Sprint <Sprint number>
Note on J3: Actual Effort - after the step has been completed a number indicating how many hours or days. This number will be used to prepare the burndown chart.
Note on K3: Use this column to provide supporting information such as changes to the original requirement.
Note on M3: This column is used to link the requirements to any resulting modules (software).
Note on N3: This column is used to link the requirements/use cases to the test scenarios.
Note on O3: This column is used to link the requirements/use cases to the test scenarios.
Note on P3: This column is used to link the requirements/use cases to the test scenarios.
When using a Scrum approach to project management, this worksheet is intended to capture the detail tasks of User Stories for the current Sprint.
Note, this is further detail of the user stories that appear on the Product Backlog sheet.

## Sprint Backlog 1
Product Backlog ID | User Story ID | User Story Task Step number | Task Step description | Assigned to | Assigned Date | Original Estimate | Adjusted estimate | Status | Actual Effort | Comment | Columns to the right are OPTIONAL depending on the level of rigor applied to the project. | Module or Component ID | Unit Test Scenario ID | System Test Scenario ID | Systems Integration Test Scenario ID
1 | USGreatOutdoor:001 | 1 | Entity Class Design | Kamal | !7-Apr-2020 | 5 hrs | 4 hrs | Completed | 3
|  | 2 | Table Design | Amrita | !6-Apr-2020 | 4 hrs | 3 hrs | Completed | 4
|  | 3 | Application Architecture | Ajesh | !6-Apr-2020 | 3 hrs | 1 hrs | Completed | 2
|  | 4 | Use case diagram | Suraj | !7-Apr-2020 | 1 hrs | 0.5 hrs | Completed | 1
|  | 5 | Sequence Diagram | Mohit | !6-Apr-2020 | 5 hrs | 4 hrs | Completed | 3
|  | 6 | Each use case detail description | Tanushree | !7-Apr-2020 | 6 hrs | 5 hrs | Completed | 6
|  | 7 | Class Layer diagram | Amrita | !6-Apr-2020 | 3 hrs | 2 hrs | Completed | 2
|  | 8 | Class Diagram | Kamal | !7-Apr-2020 | 2 hrs | 1 hrs | Completed | 1.5
|  | 9 | Webservice URL Details | Ajesh | !6-Apr-2020 | 3 hrs | 1 hrs | Completed | 2
2 | USGreatOutdoor:002 | 1 | Test plan for dao, | Mohit | !7-Apr-2020 | 3 hrs | 2 hrs | Completed | 3
|  | 2 | Test plan for service | Tanushree | !7-Apr-2020 | 4 hrs | 3 hrs | Completed | 4
|  | 3 | Test plan for webservice methods | Suraj | !7-Apr-2020 | 3 hrs | 1 hrs | Completed | 2
3 | USGreatOutdoor:003 | 1 | Creating a Spring boot starter project | Amrita | 2020-04-18 | 2 hrs | 0.5 hrs | Completed | 1.5 hrs
|  | 2 | Adding dependencies in Pom.xml and initializing it | Amrita | 2020-04-18 | 1 hrs | 0.5 hrs | Completed | 0.5 hrs
|  | 3 | Adding server, jpa properties in application.properties | Mohit | 2020-04-18 | 1 hrs | 0.5 hrs | Completed | 0.5 hrs
4 | USGreatOutdoor:004 | 1 | Entity Class Design | Kamal | 2020-04-19 | 3 hrs | 2 hrs | completed | 1.5 hrs
|  | 2 | Check tables are poulated in DB | Amrita | 2020-04-19 | 1 hrs | 1.5 hrs | complted | 45 min
|  | 3 | Populate the Data | Ajesh | 2020-04-19 | 3o min | 1 hrs | complted | 30 min
5 | USGreatOutdoor:005 | 1 | Write a JPQL query to retrieve the product details for the given search, src in DAO layer | Amrita | 2020-04-20 | 1 hrs | 45 min | complted | 45 min
|  | 2 | service method invoke the Dao and get the list of the product. If list is empty throw ProductNotFoundException "No Product Found" | Mohit | 2020-04-20 | 1 hrs | 45 min | completed | 45 min
|  | 3 | Service method will check the item in inventeryand show wishlist or aad to cart option to the user | Tanushree | 2020-04-21 | 1 hr | 50 min | complted | 30 min
|  | 4 | REstController method get the details of the product and send to service to place order | Ajesh | 2020-04-21 | 1 hr | 50 min | completed | 40 min
6 | USGreatOutdoor:006 | 1 | Write the JPQL query to get the product by product ID in DAO | Mohit | 2020-04-22 | 1 hr | 50 min | complted | 45 min
|  | 2 | Write the JPQL query to get the User by User ID in DAO | Amrita | 2020-04-23 | 1 hr | 45 min | complted | 40 min
|  | 3 | Write a code to insert placing order instance | Ajesh | 2020-04-23 | 40 min | 30 min | complted | 25 min
|  | 4 | Service checks the product id and user id and the product is available or not | Mohit | 2020-04-24 | 30 min | 25 min | Complted | 20 min
|  | 5 | If available deduts the item from the inventery | Ajesh | 2020-04-24 | 30 min | 30 min | Complted | 20 min
|  | 6 | generate the product ID and bind to added Product in the card | Ajesh | 2020-04-25 | 50 min | 45 min | Complted | 40 min
|  | 7 | RestController method get the details such as product ID, no of items, user ID and send to service method and returns card Id | Mohit | 2020-04-25 | 1 hr | 50 min | complted | 50 min
7 | USGreatOutdoor:007 | 1 | Showing Wishlist to user in this user story user can add Product to Wishlist and Remove From Wishlist. | Tanushree | 2020-04-25 | 1 hr | 1 hrs | complted | 1 hr
8 | USGreatOutdoor:008 | 1 | AddressManagement in this user can add address,delete and update address before placing the order. | Amrita | 2020-04-26 | 1.5 hrs | 1.5 hrs | complted | 1 hour20 min
9 | USGreatOutdoor:009 | 1 | Cancel Order in this user Story user can cancel order. | Suraj
10 | USGreatOutDoor:010 | 1 | Delievery Time Report | Kamal | 2020-04-25 | 1.5 hrs | 1 hrs | complted | 1 hr
11 | USGreatOutdoor:011 | 1 | Showing growth Report | Kamal | 2020-04-26 | 1.5 hrs | 1.5 hrs | complted | 1.5 hrs
List User Story steps that were not completed at Sprint End
When using a Scrum approach to project management, this worksheet is intended to capture the detail tasks of User Stories for the current Sprint.
Note, this is further detail of the user stories that appear on the Product Backlog sheet.
Note on A3: This column is used to trace each row of this spreadsheet back to a specific row on the MoSCoW List worksheet.
Note on B3: This column is used to document the Use Case Identifier.
Note on D3: Task Step description. You would only use this column when detailing User Stories using the short form as described in RA.021. If you are using the long form of the User Stories template you may eliminate this column.
Note on E3: List the Scrum team members assigned to this task.
Note on F3: Column is used to document the date the task was assigned
Note on G3: Use this column to provide Initial Scrum team estimate of effort for the task step to be completed, may be numbers of days or hours.
Note on H3: Adjusted estimate after the Sprint has begun
Note on I3: Task status: Started In Progress Completed Cancelled Deferred to Sprint <Sprint number>
Note on J3: Actual Effort - after the step has been completed a number indicating how many hours or days. This number will be used to prepare the burndown chart.
Note on K3: Use this column to provide supporting information such as changes to the original requirement.
Note on M3: This column is used to link the requirements to any resulting modules (software).
Note on N3: This column is used to link the requirements/use cases to the test scenarios.
Note on O3: This column is used to link the requirements/use cases to the test scenarios.
Note on P3: This column is used to link the requirements/use cases to the test scenarios.